## Open items
FUND NAME | [5 empty] | ITEM(S) | Fund Office | Legal | Auditor | Actuary (DB) | Actuary (Health) | Investment Consultant | Broker (Stop loss) | BOT | Exec. Committee | Other: | STATUS | COMMENT(S) | DATE PLACE ON LIST | COMPLETED DATE
DC | DB | HW |  |  |  | Retirement Guide |  | x | [5 empty] | x |  |  | Completed | Printed by Nehlsen and Received in Office | 2025-01-17
DC | DB | HW |  |  |  | Benefits Guide | [10 empty] | In progress | First draft circulated | 2025-01-17
DC | DB | HW |  |  |  | Cyber Security Policies - Procedures | x | x | x |  |  |  |  | x |  |  | In progress | Policies Completed, Procedures in progress | 2025-01-17
DC | DB | HW | SC | JATC |  | Plan Year 2024 audit | x |  | x | [7 empty] | Completed |  | 2025-09-19
DC | DB | HW | SC | JATC |  | Form 5500, Form 990, Form 990T | x | x | x |  |  |  |  | x |  |  | Completed |  | 2025-09-19
DC | DB | HW | SC | JATC |  | Legal Service Invoice |  | x | [8 empty] | ? | 4/24; 5/24; 6/24; 7/24; 8/24; 9/24; 10/24; 11/24; 12/24; 1/25; 2/25; 3/25; 4/25; 5/25; 6/25; 7/25; 8/25 | 2025-01-17
DC | DB | HW | SC |  |  | Meeting Minutes Draft |  | x | [8 empty] | ? | 6/26/19; 7/17/19; 8/29/19 | 2025-01-17
DC | [5 empty] | Purchase of a 66 2/3% J&S Annuity for Member's retirement benefit or Transfer to Pension Plan for administering benefit. |  | x | [5 empty] | x |  |  | In progress | Legal counsel to seek alternative funding source (Fund) backing for member's annuity account, mbr didn't have the required assets | 2025-01-17
DC | [5 empty] | Meeting Minutes Edit |  | x | [8 empty] | ? | 3/7/23; 7/30/25; 9/17/25 | 2025-01-17
DC | [5 empty] | Summary of Material Modification |  | x | [8 empty] | Completed | SMM for DC Plan Amendment on RMD | 2025-09-19
| DB |  |  |  |  | Determination of POA's request to direct deposit retirees benefit into their account and not members |  | x | [8 empty] | ? | Has been reviewed and Bill to send memo to Fund Office | 2025-01-17
| DB |  |  |  |  | Annual Pension Verification - 2025 Program | x | [9 empty] | In progress | 73 forms still outstanding | 2025-09-19
| DB |  |  |  |  | Outstanding DRO review for Alternate Payees |  | x | [8 empty] | In progress |  | 2025-09-19
| DB |  |  |  |  | Meeting Minutes Edit |  | x | [8 empty] | ? | 2/26/23; 5/16/23; 7/30/25; 9/17/25 | 2025-01-17
| DB |  |  |  |  | Summary of Material Modification |  | x | [8 empty] | Completed | SMM for DB Plan Amendment on RBD | 2025-09-19
| DB |  |  |  |  | Funding Percentage Review and Options |  | x |  | x |  |  |  | x |  |  | In progress | Discussed at November Board Meeting | 2025-09-19
|  | HW |  |  |  | Plan Document |  | x | [8 empty] | In progress | Draft sent to BOT & Administrator for Review | 2025-01-17
|  | HW |  |  |  | DOL Audit |  | x | [7 empty] | DOL | In progress | Legal received add'l inquiry from DOL | 2025-01-17
|  | HW |  |  |  | Contract with Sav Rx |  | x | [7 empty] | Sav Rx | In progress |  | 2025-01-17
|  | HW |  |  |  | Stop Loss Claim Denial on Member |  | x |  |  | x |  | x |  |  |  | In progress | Bill to provide outline of next steps and potential cost of pursuit of claim appeal | 2025-01-17
|  | HW |  |  |  | Annual Family Statement - 2025 Program | x | [9 empty] | In progress | 420 Statements outstanding | 2025-09-22
|  | HW |  |  |  | MAP informational mailing to members | x | [6 empty] | x |  | Ulliance |  |  | 2025-01-17
|  | HW |  |  |  | Vision Marketing | x | [9 empty] | On going |  | 2025-09-19
|  | HW |  |  |  | Mental Health Program Pricing |  |  |  |  | x | [5 empty] | In progress |  | 2025-01-17
|  | HW |  |  |  | Health Screening / Fair @ UH | x | [9 empty] | Completed | Saturday, Oct 11th - biometric screening, HW info, food trucks, bounce houses, raffles | 2025-01-17
|  | HW |  |  |  | Sav Rx mailing to members regarding mail-order | x |  |  |  | x |  |  |  |  | Sav Rx |  |  | 2025-01-17
|  | HW |  |  |  | A secondary mailing to members regarding Sav Rx | x | [11 empty] | 2025-01-24
|  | HW |  |  |  | Meeting Minutes Edit |  | x | [8 empty] | ? | 7/30/25; 9/17/25 | 2025-01-17
|  | HW |  |  |  | Contract with EyeMed |  | x | [7 empty] | EyeMed |  |  | 2025-09-19
|  | HW |  |  |  | Medical vendor review |  |  |  |  | x |  |  | x |  |  | In Progress | Strategic Planning Session | 2025-09-19
|  |  | SC |  |  | Payroll Audit Selection - Ongoing | x | [8 empty] | Novak Francella | Routine |  | 2025-01-17
|  |  | SC |  |  | Optimal Delinquencies - Lawsuit and Bond Claim |  | x | [8 empty] | In progress | Lawsuit has been filed, service attempted unsuccessful. Send to SOS for service attempt. | 2025-01-17
|  |  | SC |  |  | Provide Collection Letters & Filings on Poole & Kent, Optimal & ForAir for Fund Office Files |  | x | [8 empty] | ? |  | 2025-01-17
|  |  | SC |  |  | Development Transition / Moving Plan - Timeline | x | x | [6 empty] | x |  | In progress |  | 2025-01-17
|  |  | SC |  |  | Participation Agreement for Affiliated Entities | [8 empty] | x |  |  | Place on the February 25th Cmte Mtg agenda | 2025-01-17
|  |  | SC |  |  | Meeting Minutes Edit |  | x | [8 empty] | ? | 7/30/25; 9/17/25 | 2025-01-17
|  |  |  | JATC |  | Curriculum Coordinator Posting / Recruitment Agency Contract |  | x | [8 empty] | On hold |  | 2025-01-17
|  |  |  | JATC |  | Meeting Minutes Edit |  | x | [9 empty] | 6/3/25; 6/11/25; 6/12/25; 7/7/25; 7/16/25; 7/22/25; 8/6/25; 9/11/25; 9/30/25; 10/15/25 | 2025-01-17
|  |  |  | JATC |  | Review of Job Duties for Monica Lopez - TC requested Asst. TC position promotion | x | x | [6 empty] | x
[5 empty] | GT | Development of Construction Plan for Suite 220/240 | x | [7 empty] | x | XB Architectural |  |  | 2025-09-19
[5 empty] | GT | Renewal of lease - Suite 130 - KB Authority (6/30/26 lease end) |  | x | [7 empty] | BLG Realty Service |  |  | 2025-09-19
[5 empty] | GT | Sales Tax Submission | x | [8 empty] | BLG Realty Service | Routine | Sales tax on rentals end 10/1/25 | 2025-09-19
[5 empty] | GT | Property Tax Submission | x | [9 empty] | Routine |  | 2025-11-19
[5 empty] | GT | Proposal to Paint Interior Corridors and Emergency Stairs | x | [8 empty] | BLG Realty Service |  |  | 2025-11-19
[5 empty] | GT | Clean & Repaint HVAC support frame on roof | x | [8 empty] | BLG Realty Service |  |  | 2025-11-19

## Open - original version
Defined Contribution Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Purchase of a 66 2/3% J&S Annuity for Member's retirement benefit or Transfer to Pension Plan for administering benefit. | Legal / BOT | Ed to seek options to purchase 66 2/3% J&S. Jeff to send info to Ed. Jeff had call with Snowden Lane Partners on 2/3/25 on options for member's J&S benefit. Exec. Cmte approved Athene for mbr's J&S benefit | 2025-01-17
Retirement Guide | Legal / BOT | Legal has edits, Kenny has edit. One guide or separate guides, Julie last pass with final. | 2025-01-17
Meeting Minutes Review of 3/7/23; 12/11/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 6/26/19; 7/17/19; 8/29/19 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Cyber Security Policies - Procedures | Legal / Fund Office / Auditor / BOT |  | 2025-01-17
Valuation for PYE 12/31/24 | Acct'g / Fund Office / ISSI |  | 2025-01-17
Statements for PYE 12/31/24 | Fund Office |  | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase and Univest Bank & Trust | 2025-01-30
Defined Benefit Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Retirement Guide | Legal / BOT | Legal has edits, Kenny has edit. One guide or separate guides, Julie last pass with final. | 2025-01-17
Determination of POA's request to direct deposit retirees benefit into their account and not members | Legal | Has been reviewed and Bill to send memo to Fund Office | 2025-01-17
Acceptance of DC Fund Account Balance for J&S Retirement Benefits | Legal / BOT / Actuary |  | 2025-01-17
Withdrawal calculation letter to Kaestle Enterprises for payment | Legal / Fund Office |  | 2025-01-30
Meeting Minutes Review of 2/16/23; 5/16/23; 11/26/24; 12/11/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 6/26/19; 7/17/19; 8/29/19 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Verification Process - Ongoing Reinstatements | Fund Office |  | 2025-01-17
Cyber Security Policies - Procedures | Legal / Fund Office / Auditor / BOT |  | 2025-01-17
Valuation for PYE 12/31/24 | Fund Office / Actuary | Data Request received from Ben, sent to ISSI for needed data | 2025-01-17
Statements for PYE 12/31/24 | Fund Office | Sent to printer | 2025-01-17
Develop & Send letter to contractors with the previous year EWL amount | Fund Office / Legal / BOT |  | 2025-01-24
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase and Univest Bank & Trust | 2025-01-30
Fengate Fund IV - Most Favored Nation Side Letter | Fund Office / Legal / BOT |  | 2024-02-14
Obtain divorce decree from Broward County for Pension Applicant | Legal Counsel |  | 2024-02-11
Health & Welfare Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Plan Document | Legal | Bill to provide draft by upcoming meeting for review. Exec. Cmte mtg later to finalize | 2025-01-17
DOL Audit | DOL/ Legal | Bill received link from DOL recently to send their req'd additional documents | 2025-01-17
Contract with Sav Rx | Legal | In process with Sav Rx, not been the easiest company to deal with on contract | 2025-01-17
Stop Loss Claim Denial on Member | Legal / Stop Loss Broker | Bill to provide outline of next steps and potential cost of pursuit of claim appeal | 2025-01-17
Meeting Minutes Review of 12/11/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 6/26/19; 7/17/19; 8/29/19 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Cyber Security Policies - Procedures | Legal / Fund Office / Auditor / BOT |  | 2025-01-17
Family Statement Process - Ongoing Reinstatements | Fund Office |  | 2025-01-17
MAP informational mailing to members | Ulliance / BOT |  | 2025-01-17
Vision revised pricing for addition of safety glasses | Benefit Consultant | adding EyeMed to vendor selections | 2025-01-17
Mental Health Program Pricing | Benefit Consultant |  | 2025-01-17
Health Screening / Fair @ UH on 7/26/25 | Fund Office | Date to be moved to fall, Union to get calendar for available date | 2025-01-17
Sav Rx mailing to members regarding mail-order | Sav Rx / Benefit Consultant / Fund Office |  | 2025-01-17
A secondary mailing to members regarding Sav Rx | Fund Office |  | 2025-01-24
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase and Univest Bank & Trust | 2025-01-30
Service Corporation | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 8/2/24; 8/9/24; 8/23/24; 9/6/24; 9/13/23; 10/3/24; 10/11/24; 11/26/24; 12/11/24; 12/12/24; 12/20/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 1/10/25; 1/24/25 | Fund Office | Bill & Jeff to develop a schedule to finalize minutes | 1/17/2025; 1/24/2025
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23; 12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Payroll Audit Selection - Ongoing | Fund Office |  | 2025-01-17
PAR disclosure from Trinity & Protocol review | Legal | Bill will provide memo on PAR disclosures to Jeff & Lianet | 2025-01-17
Optimal Delinquencies - Lawsuit and Bond Claim | Legal | Lawsuit has been filed, service attempted unsuccessful. Send to SOS for service attempt. | 2025-01-17
Provide Collection Letters & Filings on Poole & Kent, Optimal & ForAir for Fund Office Files | Legal |  | 2025-01-17
Building Search & Acqusition - Ongoing | Exec Cmte / Legal / Fund Office / Actuary / Inv Consultant |  | 2025-01-17
Development of Construction / Transition / Moving Plan - Timeline | Legal / Fund Office |  | 2025-01-17
Participation Agreement for Affiliated Entities | Exec Cmte | Place on the February 25th Cmte Mtg agenda | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase and Univest Bank & Trust | 2025-01-30
Joint Apprenticeship & Training Committee Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 7/10/24; 7/11/24; 7/18/24; 8/7/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17
Meeting Minutes Drafting of 9/12/24; 10/3/24; 11/21/24; 12/16/24; 1/8/25; 1/9/25; 2/3/25 | Fund Office |  | 1/17/2025; 2/3/20205
Legal Counsel invoices for Period End of 5/31/23; 6/30/23; 7/31/23; 8/31/23; 9/30/23; 10/31/23; 11/30/23;12/31/23; 1/31/24; 2/29/24; 3/31/24; 4/30/24; 5/31/24; 6/30/24; 7/31/24; 8/31/24; 9/30/24; 10/31/24; 11/30/24;12/31/24; 1/31/25 | Legal | Bill & Jeff to develop a schedule to finalize outstanding payment | 1/17/2025; 2/5/2025
Curriculum Coordinator Posting / Recruitment Agency Contract | Legal |  | 2025-01-17
Recommendation of Cash Balances; Contribution Receivables; Capital & Operating Reserves | Acct'g / Fund Office | On Board 2/20/25 Meeting Agenda | 2025-01-17
Treasury Bank Search ~ BOA ceasing to service accounts on 6/30/25 | Fund Office | Sent Group Analysis Statements to PNC, JP Morgan Chase and Univest Bank & Trust | 2025-01-30
Missing Scholarship Loan Breach settlement payment from J. Marques | Legal |  | 2025-02-17

## Completed
Defined Contribution Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
1099R Payment & Report Reconciliation and Mailing / Filing of 1099R | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-15
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Defined Benefit Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Withdrawal calculation for Kaestle Enterprises | Actuary | Completed - On 1/29 BOT Mtg. | 2025-01-17 | 2025-01-29
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24; 11/26/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
Recalculation of Working Retirees | Fund Office | Completed | 2025-01-17 | 2025-01-26
1099R Payment & Report Reconciliation and Mailing / Filing of 1099R | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-16
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Health & Welfare Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24; | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
Implementation of Retiree Subsidy Program Increase in months & maximum amount | Fund Office | Completed | 2025-01-17 | 2025-01-20
Implementation of Stop Loss Carrier Reporting and Payment | Stop Loss Broker / Fund Office | Completed | 2025-01-17 | 2025-01-19
W-2 Payment & Report Reconciliation and Mailing / Filing of W-2 | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-24
1095B Report Reconcilation and Mailing / Filing of 1095B | Fund Office / ISSI | Completed | 2025-01-17 | 2025-01-24
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Service Corporation | Ownership of Item(s) | Notes | Date on List | Date Completed
Meeting Minutes Review of 5/22/24; 9/18/24; 10/30/24 | Legal | Bill & Jeff to develop a schedule to finalize minutes | 2025-01-17 | 2025-02-04
Implementation of 100% Payroll Records Review | Fund Office / Payroll Auditor |  | 2025-01-17 | 2025-01-30
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14
Implementation of 100% Payroll Records Review | Fund Office / Payroll Auditor | Completed | 2025-01-17 | 2025-02-18
Joint Apprenticeship & Training Committee Trust | Ownership of Item(s) | Notes | Date on List | Date Completed
Legal Counsel invoices for Period End of 4/30/23 | Legal | Completed | 2025-01-17 | 2025-02-14